## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS
4th QUARTER, CY 2019
Municipality: HERNANI, E. SAMAR
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
CDP, CLUP and CBMS and other anti-poverty programs |  | 120000 |  | 4thQ, 2019 | 0 | 353630 |  | NOT YET STARTED
Road Concreting LGU-UNDP Evacuation Center |  | 5000000 |  | 4thQ, 2019 | 0 | 4937360.4 |  | NOT YET STARTED
Construction of Senior Citizen Building |  | 1500000 |  | 4thQ, 2019 | 0 | 0 |  | NOT YET STARTED
Economic Development
Installation of booth cashier for BPLO-BOSS | Brgy.Canciledes | 200000 |  | 4thQ, 2019 | 0 | 0 |  | NOT YET STARTED
Tourism Development Program | Canhugas Nature Park, Panglaw Beach, Bura Beach, Guinduyanan Beach | 1300000 |  | 4thQ, 2019 | 0 | 1254979.08 |  | NOT YET STARTED
Tourist Information and Panapuan Center, Phase 1 | Brgy. Padang | 500000 |  | 4thQ, 2019 | 0 | 0 |  | NOT YET STARTED
Construction of Motor Pool | Brgy.Canciledes | 500000 |  | 4thQ, 2019 | 0 | 0 |  | NOT YET STARTED
Construction of municipal fence, pedestrian road, covered walk way | Brgy.Canciledes | 500000 |  | 4thQ, 2019 | 0 | 0 |  | NOT YET STARTED
Construction of public toilet at Canhugas Nature Park | Brgy.Canciledes | 300000 |  | 4thQ, 2019 | 0 | 0 |  | NOT YET STARTED
Debt Servicing for DBP |  | 0 |  | 4thQ, 2019 | 0 | 0 |  | NOT YET STARTED
NOT YET STARTED
Environmental Management
Concreting of Access Road of Municipal MRRF | Brgy. San Miguel | 300000 |  | 4thQ, 2019 | 0 | 300000 |  | NOT YET STARTED
Seaborne Patrolling |  | 50000 |  | 4thQ, 2019 | 0 | 43925 |  | NOT YET STARTED
Land Acquisition for SLF |  | 1000000 |  | 4thQ, 2019 | 0 | 0 |  | NOT YET STARTED
Purchase of Truck for Garbage Collection |  | 1463664 |  | 4thQ, 2019 | 0 | 0 |  | NOT YET STARTED
Participatory Coastal resource Asessment |  | 30000 |  | 4thQ, 2019 | 0 | 0 |  | NOT YET STARTED
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
ADELFO ABELLA |  |  |  |  | AMADO L. CANDIDO
Local Budget Officer |  |  |  |  | Local Chief Executive