## Sheet1
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
1st QUARTER, CY 2020
Province, City or Municipality: HERNANI, E. SAMAR
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
DOST-RO-08 Financial Assistance for the Processing of Agri-Products | Brgy. Canciledes | 300000 | - | - | - | -
DILG-Assistance to Municipality 2019 | Brgy. Canciledes-Atang FMR | 9466000 | Nov. 25, 2019 | - | 100% | 9466000
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ADELFO B. ABELLA |  | SYLVIA E. ALMAZAN |  |  | HON. AMADO L. CANDIDO
Local Budget Officer |  | Local Accountant |  |  | Local Chief Executive