## 20%EDF-2ndQtr2020
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS
2ND QUARTER, CY 2020
Province of Eastern Samar
Program or Project |  |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[7 empty] | % of Completion | Total Cost Incurred to Date
A. Social Development
| 1. | Construction of CT Scan Building | Eastern Samar | 5000000
| 2. | Renovation of Eastern Samar Provincial Hospital Building | Borongan City | 10000000
| 3. | Construction/Completion of Multi-Purpose Buildings | Eastern Samar | 37500000 |  |  | 1.743% | 653547.54
| 4. | Construction of New Capitol Building | Borongan City | 50000000
B. Economic Development
| 1. | Livelihood Development Program | Eastern Samar | 10000000
| 2. | Construction/Concreting of FMR, Brgy. 7 - Brgy. Cantenio | Quinapondan | 2500000
| 3. | Construction/Concreting of FMR, Brgy. Malaintos - Brgy. Sto. Niño - Dinigpian | Dolores | 6000000
| 4. | Agricultural & Fishery Program | Eastern Samar | 15000000
| 5. | Brgy. Road Opening, Farm-to-Market Road | Eastern Samar | 25000000
| 6. | Road Concreting, Brgy. Agsam - Naga FMR | Oras | 5000000
| 7. | Road Concreting, Brgy. Solong FMR | Can-avid | 5000000
| 8. | Construction/Concreting of Brgy. Road, Brgy. Dao | Oras | 2500000
| 9. | Maintenance of Provincial Roads & Bridges | Eastern Samar | 25000000
| 10. | PRDP Counterpart | Eastern Samar | 50000000
| 11. | Livestock & Poultry | Eastern Samar | 5816198
| 12. | Barangay Development Programs | Eastern Samar | 19000000
| 13. | Construction/Concreting of Brgy. Road at Brgy. Mantang | Taft | 2500000
| 14. | Construction/Concreting of FMR, Brgy. Palactad - Brgy. Sta. Margarita | Quinapondan | 2500000
| 15. | Road Concreting, Brgy. Camada - Maytigbao | Maydolong | 3000000 |  |  | 100% | 2990459.94
C. Environmental Development
| 1. | Construction of Drainage, Capitol Site | Borongan City | 5000000
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
|  | CYRIL JESUS D. ALZATE |  |  |  |  | HON. BEN P. EVARDONE
|  | Provincial Budget Officer |  |  |  |  | Provincial Governor
286316198